## Sheet1
project plan
| #sprint | Task name | Responsible |  |  | Start | End | Day | Status
1 |  | Booking |  | Abdallah |  | 2018-08-03 | 15/3/2018 | 8 | compelete
1 |  | analysis |  | adel.saleh |  | 2018-08-03 | 2018-09-03 | 2 | compelete
1 |  | design |  | Rashad |  | 2018-10-03 | 2018-11-03 | 1 | compelete
1 |  | Implement |  | moustafa |  | 2018-11-03 | 14/3/2018 | 4 | compelete
1 |  | test&maintaince |  | Eid |  | 14/3/2018 | 15/3/2018 | 1 | compelete
2 |  | Agecy |  | Eid |  | 16/3/2018 | 22/3/2018 | 8 | compelete
2 |  | analysis |  | adel |  | 16/3/2018 | 17/3/2018 | 1 | compelete
2 |  | design |  | saleh,rashad |  | 17/3/2018 | 19/3/2018 | 2 | compelete
2 |  | Implement |  | abdallah |  | 19/3/2018 | 21/3/2018 | 3 | compelete
2 |  | test&maintaince |  | moustafa |  | 21/3/2018 | 22/3/2018 | 2 | compelete